## Gantt Chart
GANTT CHART
PROJECT TITLE |  | Dental and Mouth Disease Chatbot |  |  |  |  | COMPANY NAME | [6 empty] | HealthyLife SDN BHD
PROJECT MANAGER |  | Mohd Hariz bin Abdul Malek |  |  |  |  | DATE | [6 empty] | 2020-11-11
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [17 empty] | PHASE TWO | [11 empty] | PHASE THREE | [26 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | Hariz, Meor | 2020-10-12 | 2020-10-15 | 4 | 100% | bar: WEEK 1 M to WEEK 1 R; WEEK 2 M to WEEK 2 T
1.1.1 | Project Charter Revisions | Fikrun | 2020-10-15 | 2020-10-16 | 2 | 100% | bar: WEEK 1 R to WEEK 1 F; WEEK 2 W
1.2 | Research | Meor, Fikrun | 2020-10-19 | 2020-10-23 | 5 | 100%
1.3 | Projections | Meor, Harraz | 2020-10-23 | 2020-10-27 | 5 | 100% | bar: WEEK 2 R to WEEK 3 T
1.4 | Stakeholders | Harraz, Meor | 2020-10-27 | 2020-10-29 | 3 | 100% | bar: WEEK 3 T to WEEK 3 R
1.5 | Guidelines | Harraz, Fikrun | 2020-10-29 | 2020-11-02 | 4 | 100% | bar: WEEK 3 R to WEEK 4 M
1.6 | Project Initiation | Meor, Fikrun | 2020-11-03 | 2020-11-04 | 2 | 100% | bar: WEEK 4 T to WEEK 4 W
2 | Project Definition and Planning
2.1 | Scope and Goal Setting | Hariz | 2020-11-05 | 2020-11-06 | 2 | 40% | bar: WEEK 4 R to WEEK 4 F
2.2 | Budget | Hariz, Fikrun | 2020-11-09 | 2020-11-12 | 4 | 10%
2.3 | Communication Plan | Meor | 2020-11-12 | 2020-11-13 | 2 | 0% | bar: WEEK 5 R to WEEK 5 F
2.4 | Risk Management | Harraz | 2020-11-16 | 2020-11-18 | 3 | 0% | bar: WEEK 6 M to WEEK 6 W
3 | Project Conception and Initiation
3.1 | Status and Tracking | Harraz | 2020-11-19 | 2020-11-20 | 2 | 0% | bar: WEEK 6 R to WEEK 6 F
3.2 | KPIs | Meor | 2020-11-23 | 2020-11-26 | 4 | 0% | bar: WEEK 7 M to WEEK 7 R
3.2.1 | Monitoring | Hariz | 2020-11-19 | 2020-12-25 | 37 | 0% | bar: WEEK 6 R to WEEK 12 F
3.2.2 | Forecasts | Fikrun | 2020-12-21 | 2020-12-25 | 5 | 0% | bar: WEEK 12 M to WEEK 12 F
3.3 | Project Updates | Meor, Fikrun | 2020-12-14 | 2020-12-18 | 5 | 0%
3.3.1 | Chart Updates | Hariz, Harraz | 2020-12-18 | 2020-12-22 | 5 | 0% | bar: WEEK 11 F to WEEK 12 T
4 | Project Performance / Monitoring
4.1 | Project Objectives | Hariz | 2020-12-23 | 2020-12-24 | 2 | 0% | bar: WEEK 12 W to WEEK 12 R
4.2 | Quality Deliverables | Meor | 2020-12-23 | 2020-12-24 | 2 | 0% | bar: WEEK 12 W to WEEK 12 R
4.3 | Effort and Cost Tracking | Fikrun, Hariz | 2020-12-24 | 2020-12-25 | 2 | 0% | bar: WEEK 12 R to WEEK 12 F
4.4 | Project Performance | Fikrun | 2020-12-24 | 2020-12-25 | 2 | 0% | bar: WEEK 12 R to WEEK 12 F